## Shobhit
Agile Task Board
Assigned To: | Shobhit Pitale
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Admin
Create SQL Server table named "Admin" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create AdminService using Angular for CRUD operations | 2 | 2 | mistakes with letter casing
UI- Create Angular Component & Template for "Admin Login Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Admin Page" using Bootstrap & Angular | 1.5 | 1.5
UI - Create Angular Component & Template for "Create Employee Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Edit Employee Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "Change Admin Password" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
Admin
Creating Data Access Layer for Admin CRUD operations using Entity Framework | 2 | 2.5
UI- Create Form for Admin Login using WPF | 0.5 | 0.5
UI- Create Form for "Create Employee" Page using WPF | 1 | 1
UI- Create Form for "Edit Employee" Page using WPF | 1 | 1.5
UI- Create Form for "Delete Employee" Page using WPF | 1 | 1.5
Creating Controller and Model for Admin in ASP.Net | 1.5 | 2
Performing Web optimization through bundling | 0.5 | 0.5
UI-Create View for "Admin Login" using bootstrap and css in ASP.Net MVC | 0.5 | 0.5
UI- Create Views for "Create Employee" Page using bootstrap in ASP.Net MVC | 1.5 | 2
UI- Create Views for "Edit Employee" Page using bootstrap in ASP.Net MVC | 1.5 | 2
UI- Create Views for "Delete Employee" Page using bootstrap in ASP.Net MVC | 0.5 | 0.5
Creating Wep API for Admin and consuming it in Angular Application | 3 | 3.5
Creating WCF Service for Admin and consuming it in ASP.NET MVC Application | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
Transaction
Creating Data Access Layer for Transactions using Entity Framework | 1.5 | 2
UI- Create Form for "Credit Transaction" Page using WPF | 1 | 1
UI- Create Form for "Debit Transaction" Page using WPF | 1 | 1
UI- Create Form for "Account Transfer" Page using WPF | 1 | 1.5
Creating Controller and Model for Transactions in ASP.Net | 1.5 | 1.5
Performing Web optimization through bundling | 0.5 | 0.5
UI-Create View for "Credit Transaction" using bootstrap and css in ASP.Net MVC | 1 | 1.5
UI- Create Views for "Debit Transaction" Page using bootstrap in ASP.Net MVC | 1 | 1
UI- Create Views for "Account Transfer" Page using bootstrap in ASP.Net MVC | 1.5 | 1.5
Creating Wep API for Transaction and consuming it in Angular Application | 2 | 2.5
Creating WCF Service for Transaction and consuming it in ASP.NET MVC Application | 1 | 1.5

## Siddhart
Agile Task Board
Assigned To: | Siddharth R Taklikar
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Loan
Create SQL Server table named "Loans" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations and other functionalities | 2 | 3
Prepare Test Cases using Excel MSUnit for all CRUD operations and other functionalities | 1 | 1
Preparing Excel test cases for applying for loan | 0.5 | 1
Preparing Excel test cases for searching loan | 0.5 | 0.5
Preparing Excel test cases for updating loan status | 0.5 | 1
Preparing Excel test cases for deleting applied loan | 0.5 | 0.5
Prepare Test Cases using MSUnit test cases for all CRUD operations and other functionalities | 2 | 2.5
Preparing MSunit test cases for applying for loan | 0.5 | 1
Preparing MSunit test cases for searching loan | 0.5 | 0.5
Preparing MSunit test cases for updating loan status | 0.5 | 1
Preparing MSunit test cases for deleting applied loan | 0.5 | 0.5
UI - Create LoansServices using Angular for CRUD operations and other functionalities | 2 | 3 | issues with array and object
UI - Create Angular Component & Template for "Loan Services" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Apply for Loan Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Update Loan" using Bootstrap & Angular | 2.5 | 3
UI - Create Angular Component & Template for "Delete Loan" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "Show Loan" using Bootstrap & Angular | 1 | 1.5
Creating Data Access Layer for Loans using Entity Framework | 2 | 2
UI- Form Designing for apply loan using WPF | 1 | 1.5
UI- Form Designing for searching loan using WPF | 1 | 1
UI- Form Designing for updating loan status using WPF | 1 | 1.5
UI- Form Designing for deleting loan using WPF | 1 | 1
Creating Controller and Model for loans in ASP.NET | 1.5 | 2
UI-Creating Views for for apply loan using bootstrap and css in ASP.NET MVC | 1.5 | 2
UI-Creating Views for searching an loan using bootstrap and css in ASP.NET MVC | 1 | 1
UI-Creating Views for updating loan status using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
UI-Creating Views for deleting loan using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
Creating Wep API for Loans and consuming it in Angular Application | 2 | 2.5
Creating WCF Service for Loans and consuming it in ASP.NET MVC Application | 1.5 | 2

## Ashmita
Agile Task Board
Assigned To: | Asmita Chandrakar
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Customer
Create SQL Server table named "Customer" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Preparing Excel test cases for adding customer | 0.5 | 0.5
Preparing Excel test cases for updating customer | 0.25 | 0.25
Preparing Excel test cases for searching customer | 0.25 | 0.25
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issue with routing
Preparing MSunit test cases for adding customer | 1 | 1.5
Preparing MSunit test cases for updating customer | 0.5 | 0.5
Preparing MSunit test cases for searching customer | 0.5 | 0.5
UI - Create CustomerService using Angular for CRUD operations | 1 | 1.5
UI - Create Angular Component & Template for "Customers Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Add Customer Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Update Customer Page" using Bootstrap & Angular | 1 | 2
Creating Data Access Layer for Customer using Entity Framework | 2 | 2
UI- Form Designing for adding customer using WPF | 1 | 1.5
UI- Form Designing for searching customer using WPF | 1 | 1
UI- Form Designing for updating Customer details using WPF | 1 | 1.5
Creating Controller and Model for Customer in ASP.NET | 1.5 | 2
UI-Creating Views for adding a customer using bootstrap and css in ASP.NET MVC | 1.5 | 2
UI-Creating Views for Searching a customer using bootstrap and css in ASP.NET MVC | 1 | 1
UI-Creating Views for Updating customer details using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
Creating Wep API for Accounts and consuming it in Angular Application | 2 | 2.5
Creating WCF Service for Accounts and consuming it in ASP.NET MVC Application | 1.5 | 2

## Akash
Agile Task Board
Assigned To: | Akash Singh
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Accounts
Create SQL Server table named "RegularAccount" and "FixedAccount" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Preparing Excel test cases for creating account | 0.25 | 0.25
Preparing Excel test cases for updating account | 0.25 | 0.5
Preparing Excel test cases for closing account | 0.25 | 0.25
Preparing Excel test cases for searching account | 0.25 | 0.5
Preparing Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
Preparing MSunit test cases for creating account | 0.5 | 0.5 | Issues with concepts and mistakes with letter casing
Preparing MSUnit test cases for updating account | 0.5 | 0.5
Preparing MSUnit test cases for closing account | 0.5 | 0.5
Preparing MSUnit test cases for searching account | 0.5 | 1
UI - Create AccountsService using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Create Account Page for existing Customer" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Update/Modify Account" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Account Page" using Bootstrap & Angular | 1 | 2
UI-Creating tab control for Regular Accounts using WPF | 1 | 1
UI-Creating tab control for Fixed Accounts using WPF | 1 | 1
UI- Form Designing for creating Account using WPF | 1 | 1.5
UI- Form Designing for searching Account using WPF | 1 | 1
UI- Form Designing for updating Account using WPF | 1 | 1.5
UI- Form Designing for closing Account using WPF | 1 | 1
Creating Controller and Model for Accounts in ASP.NET | 1.5 | 2
UI-Creating Views for Creating an account using bootstrap and css in ASP.NET MVC | 1.5 | 2
UI-Creating Views for Searching an account using bootstrap and css in ASP.NET MVC | 1 | 1
UI-Creating Views for Updating an account using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
UI-Creating Views for Closing an account using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
Creating Wep API for Accounts and consuming it in Angular Application | 2 | 2.5
Creating WCF Service for Accounts and consuming it in ASP.NET MVC Application | 1.5 | 2

## Tarunsree
Agile Task Board
Assigned To: | Tarunsree
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Debit Card
Create SQL Server table named "DebitCard" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Preparing Excel test cases for applying for debit card
Preparing Excel test cases for searching debit card
Preparing Excel test cases for updating debit card
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3 | Issues in concepts and mistakes in letter casing
Preparing MSunit test cases for applying for debit card
Preparing MSunit test cases for searching debit card
Preparing MSunit test cases for updating debit card
UI - Create UtilitiesService using Angular for CRUD operations | 2 | 2
UI - Create Angular Component & Template for "DebitCard" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Add DebitCard Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Update DebitCard Status Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Search DebitCard" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Display List Of Debit Cards" using Bootstrap & Angular | 2 | 2.5
UI- Form Designing for appling for debit card using WPF | 1 | 1.5
UI- Form Designing for searching debit card using WPF | 1 | 1
UI- Form Designing for updating debit card using WPF | 1 | 1.5
UI- Form Designing for closing Account using WPF | 1 | 1
Creating Controller and Model for Accounts in ASP.NET | 1.5 | 2
UI-Creating Views for Creating an account using bootstrap and css in ASP.NET MVC | 1.5 | 2
UI-Creating Views for Searching an account using bootstrap and css in ASP.NET MVC | 1 | 1
UI-Creating Views for Updating an account using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
UI-Creating Views for Closing an account using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
Creating Wep API for Accounts and consuming it in Angular Application | 2 | 2.5
Creating WCF Service for Accounts and consuming it in ASP.NET MVC Application | 1.5 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
Cheque Book
Create SQL Server table named "ChequeBook" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Preparing Excel test cases for applying for debit card | 2 | 2.5 | Issues in concepts and mistakes in letter casing
Preparing Excel test cases for searching debit card | 2 | 2
Preparing Excel test cases for updating debit card | 2 | 2
Prepare Test Cases using MSUnit test cases for all CRUD operations | 3 | 3
Preparing MSunit test cases for applying for Cheque Book | 2 | 2
Preparing MSunit test cases for searching Cheque Book | 2 | 2
Preparing MSunit test cases for updating Cheque Book | 2 | 2
UI - Create UtilitiesService using Angular for CRUD operations
UI - Create Angular Component & Template for "ChequeBook" using Bootstrap & Angular
UI-Create Angular Component & Template for "Add ChequeBook Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Update ChequeBook Status Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Search ChequeBook Based On AccountId" using Bootstrap & Angular
UI - Create Angular Component & Template for "Display List Of All Cheque Books" using Bootstrap & Angular
UI- Form Designing for creating Account using WPF | 1 | 1.5
UI- Form Designing for searching Account using WPF | 1 | 1
UI- Form Designing for updating Account using WPF | 1 | 1.5
UI- Form Designing for closing Account using WPF | 1 | 1
Creating Controller and Model for Accounts in ASP.NET | 1.5 | 2
UI-Creating Views for Creating an account using bootstrap and css in ASP.NET MVC | 1.5 | 2
UI-Creating Views for Searching an account using bootstrap and css in ASP.NET MVC | 1 | 1
UI-Creating Views for Updating an account using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
UI-Creating Views for Closing an account using bootstrap and css in ASP.NET MVC | 0.5 | 0.5
Creating Wep API for Accounts and consuming it in Angular Application | 2 | 2.5
Creating WCF Service for Accounts and consuming it in ASP.NET MVC Application | 1.5 | 2