## Shobit
Agile Task Board
Assigned To: | Shobhit Pitale
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Admin
Create SQL Server table named "Admin" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create AdminService using Angular for CRUD operations | 2 | 2 | mistakes with letter casing
UI- Create Angular Component & Template for "Admin Login Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Admin Page" using Bootstrap & Angular | 1.5 | 1.5
UI - Create Angular Component & Template for "Create Employee Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Edit Employee Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "Change Admin Password" using Bootstrap & Angular | 1 | 2

## Siddhart
Agile Task Board
Assigned To: | Siddharth R Taklikar
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Loan
Create SQL Server table named "Loans" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations and other functionalities | 2 | 3
Prepare Test Cases using Excel MSUnit for all CRUD operations and other functionalities | 1 | 1
Preparing Excel test cases for applying for loan
Preparing Excel test cases for searching loan
Preparing Excel test cases for updating loan status
Preparing Excel test cases for deleting applied loan
Prepare Test Cases using MSUnit test cases for all CRUD operations and other functionalities | 2 | 2.5
Preparing MSunit test cases for adding customer
Preparing MSunit test cases for adding customer
Preparing MSunit test cases for adding customer
Preparing MSunit test cases for deleting applied loan
UI - Create LoansServices using Angular for CRUD operations and other functionalities | 2 | 3 | issues with array and object
UI - Create Angular Component & Template for "Loan Services" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Apply for Loan Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Update Loan" using Bootstrap & Angular | 2.5 | 3
UI - Create Angular Component & Template for "Delete Loan" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "Show Loan" using Bootstrap & Angular | 1 | 1.5
Creating Data Access Layer for Loan using Entity Framework
UI- Form Designing of window forms for Loan
Performing CRUD operations using stored procedures and LINQ queries
UI-Creating Views for Applying,Searching,Deleting,Updating the loan status using bootstrap and css
Performing Web optimization through bundling
Writing the C# Controller code for Loan
Creating Wep API and consuming it in Angular Application
Creating WCF Service and consuming it in ASP.NET MVC Application

## Ashmita
Agile Task Board
Assigned To: | Asmita Chandrakar
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Customer
Create SQL Server table named "Customer" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Preparing Excel test cases for adding customer
Preparing Excel test cases for updating customer
Preparing Excel test cases for searching customer
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issue with routing
Preparing MSunit test cases for adding customer
Preparing MSunit test cases for updating customer
Preparing MSunit test cases for searching customer | 2 | 3
UI - Create CustomerService using Angular for CRUD operations | 1 | 1.5
UI - Create Angular Component & Template for "Customers Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Add Customer Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Update Customer Page" using Bootstrap & Angular | 1 | 2
Creating Data Access Layer for Customer using Entity Framework
UI- Form Designing of window forms for Customer
Performing CRUD operations using stored procedures and LINQ queries
UI-Creating Views for Creating,Searching,Updating customer using bootstrap and css
Performing Web optimization through bundling
Writing the C# Controller code for Customer
Creating Wep API and consuming it in Angular Application
Creating WCF Service and consuming it in ASP.NET MVC Application

## Akash
Agile Task Board
Assigned To: | Akash Singh
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Accounts
Create SQL Server table named "RegularAccount" and "FixedAccount" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Preparing Excel test cases for creating account
Preparing Excel test cases for updating account
Preparing Excel test cases for closing account
Preparing Excel test cases for searching account
Preparing Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
Preparing MSunit test cases for creating account
Preparing MSUnit test cases for updating account
Preparing MSUnit test cases for closing account
Preparing MSUnit test cases for searching account
UI - Create AccountsService using Angular for CRUD operations | 2 | 2.5 | issue with concept and mistakes in character casing
UI - Create Angular Component & Template for "Create Account Page for existing Customer" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Create Account Page for new Customer" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Update/Modify Account" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Account Page" using Bootstrap & Angular | 1 | 2
Creating Data Access Layer for Accounts using Entity Framework
UI- Form Designing of window forms for Accounts
Performing CRUD operations using stored procedures and LINQ queries
UI-Creating Views for Creating,Searching,Updating and deleting an account using bootstrap and css
Performing Web optimization through bundling
Writing the C# Controller code for Accounts
Creating Wep API and consuming it in Angular Application
Creating WCF Service and consuming it in ASP.NET MVC Application

## Tarunsree
Agile Task Board
Assigned To: | Tarunsree
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Debit Card
Create SQL Server table named "DebitCard" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Preparing Excel test cases for applying for debit card
Preparing Excel test cases for searching debit card
Preparing Excel test cases for updating debit card
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
Preparing MSunit test cases for applying for debit card
Preparing MSunit test cases for searching debit card
Preparing MSunit test cases for updating debit card
UI - Create UtilitiesService using Angular for CRUD operations | 2 | 2 | issue with concept and mistakes in character casing
UI - Create Angular Component & Template for "DebitCard" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Add DebitCard Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Update DebitCard Status Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Search DebitCard" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Display List Of Debit Cards" using Bootstrap & Angular | 2 | 2.5
Creating Data Access Layer for Debit Card using Entity Framework
UI- Form Designing of window forms for Debit Card
Performing CRUD operations using stored procedures and LINQ queries
UI-Creating Views for Creating,Searching,Updating and deleting an account using bootstrap and css
Performing Web optimization through bundling
Writing the C# Controller code for Debit Card
Creating Wep API and consuming it in Angular Application
Creating WCF Service and consuming it in ASP.NET MVC Application
Task | Actual No. of Hours Expected | Actual No. of Hours
Cheque Book
Create SQL Server table named "ChequeBook" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Preparing Excel test cases for applying for debit card | 2 | 2.5
Preparing Excel test cases for searching debit card | 2 | 2
Preparing Excel test cases for updating debit card | 2 | 2 | issue with concept and mistakes in character casing
Prepare Test Cases using MSUnit test cases for all CRUD operations | 3 | 3
Preparing MSunit test cases for applying for Cheque Book | 2 | 2
Preparing MSunit test cases for searching Cheque Book | 2 | 2
Preparing MSunit test cases for updating Cheque Book | 2 | 2
UI - Create UtilitiesService using Angular for CRUD operations
UI - Create Angular Component & Template for "ChequeBook" using Bootstrap & Angular
UI-Create Angular Component & Template for "Add ChequeBook Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Update ChequeBook Status Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Search ChequeBook Based On AccountId" using Bootstrap & Angular
UI - Create Angular Component & Template for "Display List Of All Cheque Books" using Bootstrap & Angular
Creating Data Access Layer for Cheque Book using Entity Framework
UI- Form Designing of window forms for Cheque Book
Performing CRUD operations using stored procedures and LINQ queries
UI-Creating Views for Creating,Searching,Updating and deleting an account using bootstrap and css
Performing Web optimization through bundling
Writing the C# Controller code for Cheque Book
Creating Wep API and consuming it in Angular Application
Creating WCF Service and consuming it in ASP.NET MVC Application